## DFMEA Template
↓ EXAMPLE ROWS — delete these before adding your own data ↓
Item | Function | Failure Mode | Failure Effect | Severity | Failure Cause | Current Prevention Control | Occurrence | Current Detection Control | Detection | RPN | Recommended Action | Action Owner | Target Date | Action Taken | Actual Completion Date | Revised Severity | Revised Occurrence | Revised Detection | Revised RPN
Housing Bore | Support main bearing under radial load | Bore diameter oversize | Bearing retention insufficient — axial slip under load | 8 | Boring bar insert worn beyond change interval | Insert change log tracked per WI-014 | 4 | Air gauge bore diameter 100% | 3 | 72 | Replace insert and re-machine bore | J. Smith | 2026-07-01
Cover Plate Face | Seal gearbox from contamination ingress | Flatness out of spec | Oil leak at mating face under vibration | 5 | Milling fixture clamp worn — workpiece lifts during cut | Fixture clamp torque verify per setup sheet SS-022 | 11 | Flatness check with dial gauge at 4 points | 5 | 275 | Replace fixture clamp; verify re-machined flatness | L. Chen | 2026-07-15
Lubrication Port | Direct oil flow to main bearing cavity | Port blocked by swarf | Oil starvation — bearing seizure; vehicle loss of drive | 9 | Coolant flow insufficient for chip clearance at feed rate | Coolant flow rate check at startup per WI-055 | 4 | Borescope inspection at final assembly | 5 | 180